## Overview
Section | Details
Project | LLM-Augmented Customer Support Triage + Quality Monitoring MVP
Current Status | Implemented and runnable as FastAPI-based MVP
Primary Goal | Automate triage and monitor response quality end-to-end
Deliverables | app.py, pipeline.py, config.py, requirements.txt, sample_payloads.json, README.md, IMPLEMENTATION_REPORT.md, IMPLEMENTATION_CHANGELOG.xlsx
Run Command | uvicorn app:app --reload
Docs URL | http://127.0.0.1:8000/docs
Verification | py_compile passed, linter diagnostics clean

## Files_Changed
File | Change Type | What Was Added/Changed | Why It Matters | Workflow Stage
requirements.txt | New file | FastAPI, Uvicorn, Pydantic, python-dotenv dependencies | Enables API service runtime | Infrastructure
config.py | New file | Central settings for SLA, quality threshold, sentiment cutoff | Centralized policy control | Policy & Config
pipeline.py | New file | Priority/category/sentiment/routing + quality checks + orchestration | Core decision engine | Triage + QA Engine
app.py | New file | FastAPI endpoints: /health, /triage, /quality, /pipeline | Exposes service for clients/integrations | API Layer
sample_payloads.json | New file | Example request payloads for all endpoints | Supports testing and demos | Testing & Onboarding
README.md | New file | End-to-end explanation + diagrams + API contract + runbook | Stakeholder understanding and handoff | Documentation
IMPLEMENTATION_REPORT.md | New file | Formal change report and coverage matrix | Auditability of submitted work | Governance/Reporting

## Endpoints
Endpoint | Method | Input | Output | Purpose | Status
/health | GET | None | {"status":"ok"} | Service health check | Implemented
/triage | POST | {ticket_text} | {priority, category, sentiment_score, routed_team, rationale} | Run triage only | Implemented
/quality | POST | {ticket_text, agent_response} | {score, passed, checks, coaching_feedback} | Evaluate agent response quality | Implemented
/pipeline | POST | {ticket_text, draft_agent_response} | {ticket_text, triage, quality, recommended_sla_minutes} | Run full end-to-end workflow | Implemented

## Workflow_E2E
Step # | Workflow Step | Code Reference | Decision/Output | Implemented?
1 | Receive ticket request | app.py (/triage, /pipeline) | Ticket text accepted | Yes
2 | Priority classification | pipeline.py::classify_priority | critical/high/medium/low | Yes
3 | Category detection | pipeline.py::classify_category | billing/authentication/technical_bug/feature_request/general_inquiry | Yes
4 | Sentiment scoring | pipeline.py::sentiment_score | Score between -1 and 1 | Yes
5 | Routing policy | pipeline.py::route_team | Queue/team assignment | Yes
6 | Agent draft quality checks | pipeline.py::evaluate_response | Quality score + pass/fail + feedback | Yes
7 | Consolidated response | pipeline.py::run_end_to_end | Merged triage + quality payload | Yes
8 | Visual documentation | README.md (Mermaid diagrams) | Architecture/flow/sequence/pipeline views | Yes

## Validation
Check | Command/Method | Result | Notes
Python syntax validation | python3 -m py_compile app.py pipeline.py config.py | Pass | No compile errors
Lint diagnostics | ReadLints on edited files | Pass | No linter errors found
API docs availability | Open /docs after uvicorn start | Ready | Not executed in this workbook run

## Open_Gaps
Gap | Impact | Current State | Next Action
PDF section-level traceability | Cannot map line-by-line to original proposal headings | Blocked by PDF MCP directory permissions | Move/copy PDF to allowed directory and extract text
Persistent data storage | No historical trend analytics | Not implemented | Add DB models and persistence layer
API auth and access controls | Service not production-hardened | Not implemented | Add auth middleware/token validation
Monitoring and observability | Limited runtime visibility | Not implemented | Add logs, metrics, traces, alerts
Ticket platform integrations | No live upstream/downstream sync | Not implemented | Add connectors (Zendesk/Freshdesk/etc.)
Evaluation benchmark suite | No measurable model-quality baseline | Not implemented | Add test set and scoring harness